## User Interface
Hours Estimated | Days (Adj) | Time Spent | Over-Under | Use Case | Important Notes | 5.5 | Productivity Factor
General
0.5 | 0.090909 |  |  | 1.1. Condominium User Login (Condominium Council Member or Condominium Building Unit Owner)
1.5 | 0.27273 |  |  | 1.2. Select Condominium Building Page
3.5 | 0.63636 |  |  | 1.3. Request Access to Condominium Building with Existing User Account
2 | 0.36364 |  |  | 1.4. Create New User Account and Request Access to Condominium Building
Total Hours Estimate | 7.5
Total Days (Adj) | 1.3636
Condominium Building and Unit Registration
1 | 0.18182 |  |  | 2.1. View Condominium Building and Unit Registration Page
3.5 | 0.63636 |  |  | 2.2. Create New Condominium Building
1.5 | 0.27273 |  |  | 2.3. View/Edit Existing Condominium Building
1.5 | 0.27273 |  |  | 2.3.1. Edit Condominium Building Photos
0.5 | 0.090909 |  |  | 2.3.2. Archive Condominium Building
0 | 0 |  |  | 2.3.2.1. Send Condominium Building to Trash
2 | 0.36364 |  |  | 2.3.3. Edit Condominium Building Units
2 | 0.36364 |  |  | 2.3.3.1. New Condominium Building Unit
0 | 0 |  |  | 2.3.3.2. Import Condominium Building Units from CSV
2 | 0.36364 |  |  | 2.3.3.3. View/Edit Existing Condominium Building Unit
2 | 0.36364 |  |  | 2.3.3.4. Edit Condominium Building Unit Photos
0.5 | 0.090909 |  |  | 2.3.3.5. Archive Condominium Building Unit
0 | 0 |  |  | 2.3.3.6. Send Condominium Building Unit to Trash
2 | 0.36364 |  |  | 2.3.4. Search Archived Condominium Buildings
0.5 | 0.090909 |  |  | 2.3.5. Unarchive Archived Condominium Building
Total Hours Estimate | 19
Total Days (Adj) | 3.4545
Condominium Information Management
1 | 0.18182 |  |  | 3.1. View Condominium Information Sections
1 | 0.18182 |  |  | 3.1.1. View All Non-Purchasable Documents for Condominium Information Section
1 | 0.18182 |  |  | 3.1.1.1. Edit Non-Purchasable Document
0.5 | 0.090909 |  |  | 3.1.1.2. Remove Non-Purchasable Document
1.5 | 0.27273 |  |  | 3.1.1.3. Add New Non-Purchasable Document
0 | 0 |  |  | 3.1.2. Add Condominium Information Section
0 | 0 |  |  | 3.1.3. Edit Condominium Information Section
0 | 0 |  |  | 3.1.4. Archive Condominium Information Section
1 | 0.18182 |  |  | 3.2. View Purchasable Document Categories
2 | 0.36364 |  |  | 3.2.1. View All Purchasable Documents for Purchasable Document Category
1.5 | 0.27273 |  |  | 3.2.1.1. Edit Purchasable Document
0.5 | 0.090909 |  |  | 3.2.1.2. Archive Purchasable Document
3 | 0.54545 |  |  | 3.2.1.3. Add New Purchasable Document
1 | 0.18182 |  |  | 3.3. View Important Contacts
1.5 | 0.27273 |  |  | 3.3.1. Add Important Contact
1 | 0.18182 |  |  | 3.3.2. View/Modify Important Contact
0.5 | 0.090909 |  |  | 3.3.3. Remove Important Contact
2 | 0.36364 |  |  | 3.4. View Condo Document Orders Report
2 | 0.36364 |  |  | 3.4.1. View Condo Document Order Details
Total Hours Estimate | 21
Total Days (Adj) | 3.8182
Condominium Building User Access Management
1.5 | 0.27273 |  |  | 4.1. Edit Assigned Condominium Building Users
1 | 0.18182 |  |  | 4.1.1. Show Pending Users (Currently in the Requested Condominium Access Queue)
0.5 | 0.090909 |  |  | 4.1.1.1. Approve Requested Access to Condominium Building
0.5 | 0.090909 |  |  | 4.1.1.2. Deny Requested Access to Condominium Building
1 | 0.18182 |  |  | 4.1.2. Show Active Users
0 | 0 |  |  | 4.1.2.1. Deactivate Condominium Building User
1 | 0.18182 |  |  | 4.1.3. Show Inactive Users
0 | 0 |  |  | 4.1.3.1. Activate Inactive Condominium Council Member/Condominium Building Unit Owner
Total Hours Estimate | 5.5
Total Days (Adj) | 1
Condominium Building Search
6 | 1.0909 |  |  | 5.1. Search for Condominium Building
Total Hours Estimate | 6
Total Days (Adj) | 1.0909
Condominium Building Viewing (Public View)
8 | 1.4545 |  |  | 6.1. View Condominium Building Information
6 | 1.0909 |  |  | 6.2. View Condominium Building Rental Unit Information
1.5 | 0.27273 |  |  | 6.2.1. Submit Contact Inquiry to Rental Agent
5 | 0.90909 |  |  | 6.3. View Condominium Building Unit for Sale Information
1 | 0.18182 |  |  | 6.3.1. Submit Contact Inquiry to Purchase Agent
5 | 0.90909 |  |  | 6.4. Order Condominium Documents | Includes searching for Condominium building
7 | 1.2727 |  |  | 6.4.1. Select Document(s) to Order
2 | 0.36364 |  |  | 6.4.2. Pay for Document(s)
1 | 0.18182 |  |  | 6.4.3. Download Document(s)
Total Hours Estimate | 36.5
Total Days (Adj) | 6.6364
Condominium Building Viewing (Condominium Building Unit Owner View)
7 | 1.2727 |  |  | 7.1. View Condominium Information for Condominium Building | Includes all Condominium sections and important contacts
0 | 0 |  |  | 7.1.1. Download Condominium Documents for Viewing Purposes
Total Hours Estimate | 7
Total Days (Adj) | 1.2727
Condominium Building Viewing (Condominium Council Member View)
2 | 0.36364 |  |  | 8.1. View Condominium Information for Condominium Building
0 | 0 |  |  | 8.1.1. Download Condominium Documents for Viewing Purposes
Total Hours Estimate | 2
Total Days (Adj) | 0.36364
Building Information Reporting
2 | 0.36364 |  |  | 9.1. Generate Building Summary Report (Enhanced Version)
2 | 0.36364 |  |  | 9.1.1. Generate Rental Building Summary Report
2 | 0.36364 |  |  | 9.1.2. Generate Condominium Building Summary Report
2 | 0.36364 |  |  | 9.1.3. Generate Commercial Building Report
3 | 0.54545 |  |  | 9.1.4. E-mail Summary Report
1 | 0.18182 |  |  | 9.1.5. Export Summary Report to CSV
2 | 0.36364 |  |  | 9.1.6. Print Summary Report
Total Hours Estimate | 14
Total Days (Adj) | 2.5455
Modifications to Existing Gateway Functionality
0 | 0 |  |  | 10.1. Archive Residential Rental Building or Residential Building Unit
0.5 | 0.090909 |  |  | 10.2. Send Residential Rental Building to Trash
Total Hours Estimate | 0.5
Total Days (Adj) | 0.090909

## Database
Hours Estimated | Days (Adj) | Time Spent | Over-Under | Use Case | 5.5 | Productivity Factor
General
0.5 | 0.090909 |  |  | 1.1. Condominium User Login (Condominium Council Member or Condominium Building Unit Owner)
2 | 0.36364 |  |  | 1.2. Select Condominium Building Page
3 | 0.54545 |  |  | 1.3. Request Access to Condominium Building with Existing User Account
2 | 0.36364 |  |  | 1.4. Create New User Account and Request Access to Condominium Building
Total Hours Estimate | 7.5
Total Days (Adj) | 1.3636
Condominium Building and Unit Registration
1.5 | 0.27273 |  |  | 2.1. View Condominium Building and Unit Registration Page
2.5 | 0.45455 |  |  | 2.2. Create New Condominium Building
2 | 0.36364 |  |  | 2.3. View/Edit Existing Condominium Building
2 | 0.36364 |  |  | 2.3.1. Edit Condominium Building Photos
0.5 | 0.090909 |  |  | 2.3.2. Archive Condominium Building
1 | 0.18182 |  |  | 2.3.2.1. Send Condominium Building to Trash
2 | 0.36364 |  |  | 2.3.3. Edit Condominium Building Units
1.5 | 0.27273 |  |  | 2.3.3.1. New Condominium Building Unit
6 | 1.0909 |  |  | 2.3.3.2. Import Condominium Building Units from CSV
2 | 0.36364 |  |  | 2.3.3.3. View/Edit Existing Condominium Building Unit
2 | 0.36364 |  |  | 2.3.3.4. Edit Condominium Building Unit Photos
0.5 | 0.090909 |  |  | 2.3.3.5. Archive Condominium Building Unit
0.5 | 0.090909 |  |  | 2.3.3.6. Send Condominium Building Unit to Trash
2 | 0.36364 |  |  | 2.3.4. Search Archived Condominium Buildings
0.5 | 0.090909 |  |  | 2.3.5. Unarchive Archived Condominium Building
Total Hours Estimate | 26.5
Total Days (Adj) | 4.8182
Condominium Information Management
1 | 0.18182 |  |  | 3.1. View Condominium Information Sections
1 | 0.18182 |  |  | 3.1.1. View All Non-Purchasable Documents for Condominium Information Section
2 | 0.36364 |  |  | 3.1.1.1. Edit Non-Purchasable Document
1 | 0.18182 |  |  | 3.1.1.2. Remove Non-Purchasable Document
1 | 0.18182 |  |  | 3.1.1.3. Add New Non-Purchasable Document
0 | 0 |  |  | 3.1.2. Add Condominium Information Section
0 | 0 |  |  | 3.1.3. Edit Condominium Information Section
0 | 0 |  |  | 3.1.4. Archive Condominium Information Section
1 | 0.18182 |  |  | 3.2. View Purchasable Document Categories
2 | 0.36364 |  |  | 3.2.1. View All Purchasable Documents for Purchasable Document Category
2.5 | 0.45455 |  |  | 3.2.1.1. Edit Purchasable Document
1 | 0.18182 |  |  | 3.2.1.2. Archive Purchasable Document
1.5 | 0.27273 |  |  | 3.2.1.3. Add New Purchasable Document
1 | 0.18182 |  |  | 3.3. View Important Contacts
1.5 | 0.27273 |  |  | 3.3.1. Add Important Contact
2.5 | 0.45455 |  |  | 3.3.2. View/Modify Important Contact
1 | 0.18182 |  |  | 3.3.3. Remove Important Contact
3 | 0.54545 |  |  | 3.4. View Condo Document Orders Report
1.5 | 0.27273 |  |  | 3.4.1. View Condo Document Order Details
Total Hours Estimate | 24.5
Total Days (Adj) | 4.4545
Condominium Building User Access Management
1.5 | 0.27273 |  |  | 4.1. Edit Assigned Condominium Building Users
0.5 | 0.090909 |  |  | 4.1.1. Show Pending Users (Currently in the Requested Condominium Access Queue)
1 | 0.18182 |  |  | 4.1.1.1. Approve Requested Access to Condominium Building
0.5 | 0.090909 |  |  | 4.1.1.2. Deny Requested Access to Condominium Building
0.5 | 0.090909 |  |  | 4.1.2. Show Active Users
0.5 | 0.090909 |  |  | 4.1.2.1. Deactivate Condominium Building User
0.5 | 0.090909 |  |  | 4.1.3. Show Inactive Users
0.5 | 0.090909 |  |  | 4.1.3.1. Activate Inactive Condominium Council Member/Condominium Building Unit Owner
Total Hours Estimate | 5.5
Total Days (Adj) | 1
Condominium Building Search
3.5 | 0.63636 |  |  | 5.1. Search for Condominium Building
Total Hours Estimate | 3.5
Total Days (Adj) | 0.63636
Condominium Building Viewing (Public View)
3 | 0.54545 |  |  | 6.1. View Condominium Building Information
2.5 | 0.45455 |  |  | 6.2. View Condominium Building Rental Unit Information
0 | 0 |  |  | 6.2.1. Submit Contact Inquiry to Rental Agent
2 | 0.36364 |  |  | 6.3. View Condominium Building Unit for Sale Information
0 | 0 |  |  | 6.3.1. Submit Contact Inquiry to Purchase Agent
2.5 | 0.45455 |  |  | 6.4. Order Condominium Documents
5 | 0.90909 |  |  | 6.4.1. Select Document(s) to Order
3 | 0.54545 |  |  | 6.4.2. Pay for Document(s)
3 | 0.54545 |  |  | 6.4.3. Download Document(s)
Total Hours Estimate | 21
Total Days (Adj) | 3.8182
Condominium Building Viewing (Condominium Building Unit Owner View)
3.5 | 0.63636 |  |  | 7.1. View Condominium Information for Condominium Building
0 | 0 |  |  | 7.1.1. Download Condominium Documents for Viewing Purposes
Total Hours Estimate | 3.5
Total Days (Adj) | 0.63636
Condominium Building Viewing (Condominium Council Member View)
1 | 0.18182 |  |  | 8.1. View Condominium Information for Condominium Building
0 | 0 |  |  | 8.1.1. Download Condominium Documents for Viewing Purposes
Total Hours Estimate | 1
Total Days (Adj) | 0.18182
Building Information Reporting
1 | 0.18182 |  |  | 9.1. Generate Building Summary Report (Enhanced Version)
3 | 0.54545 |  |  | 9.1.1. Generate Rental Building Summary Report
3 | 0.54545 |  |  | 9.1.2. Generate Condominium Building Summary Report
3 | 0.54545 |  |  | 9.1.3. Generate Commercial Building Report
0 | 0 |  |  | 9.1.4. E-mail Summary Report
0 | 0 |  |  | 9.1.5. Export Summary Report to CSV
0 | 0 |  |  | 9.1.6. Print Summary Report
Total Hours Estimate | 10
Total Days (Adj) | 1.8182
Modifications to Existing Gateway Functionality
0 | 0 |  |  | 10.1. Archive Residential Rental Building or Residential Building Unit
1.5 | 0.27273 |  |  | 10.2. Send Residential Rental Building to Trash
Total Hours Estimate | 1.5
Total Days (Adj) | 0.27273

## Business Logic
Hours Estimated | Days (Adj) | Time Spent | Over-Under | Use Case | 5.5 | Productivity Factor
General
0.5 | 0.090909 |  |  | 1.1. Condominium User Login (Condominium Council Member or Condominium Building Unit Owner)
2 | 0.36364 |  |  | 1.2. Select Condominium Building Page
2.5 | 0.45455 |  |  | 1.3. Request Access to Condominium Building with Existing User Account
3 | 0.54545 |  |  | 1.4. Create New User Account and Request Access to Condominium Building
Total Hours Estimate | 8
Total Days (Adj) | 1.4545
Condominium Building and Unit Registration
6 | 1.0909 |  |  | 2.1. View Condominium Building and Unit Registration Page
4.5 | 0.81818 |  |  | 2.2. Create New Condominium Building
4 | 0.72727 |  |  | 2.3. View/Edit Existing Condominium Building
5 | 0.90909 |  |  | 2.3.1. Edit Condominium Building Photos
1 | 0.18182 |  |  | 2.3.2. Archive Condominium Building
2 | 0.36364 |  |  | 2.3.2.1. Send Condominium Building to Trash
4 | 0.72727 |  |  | 2.3.3. Edit Condominium Building Units
3 | 0.54545 |  |  | 2.3.3.1. New Condominium Building Unit
10 | 1.8182 |  |  | 2.3.3.2. Import Condominium Building Units from CSV
4 | 0.72727 |  |  | 2.3.3.3. View/Edit Existing Condominium Building Unit
3 | 0.54545 |  |  | 2.3.3.4. Edit Condominium Building Unit Photos
0.5 | 0.090909 |  |  | 2.3.3.5. Archive Condominium Building Unit
0.5 | 0.090909 |  |  | 2.3.3.6. Send Condominium Building Unit to Trash
2 | 0.36364 |  |  | 2.3.4. Search Archived Condominium Buildings
0.5 | 0.090909 |  |  | 2.3.5. Unarchive Archived Condominium Building
Total Hours Estimate | 50
Total Days (Adj) | 9.0909
Condominium Information Management
2.5 | 0.45455 |  |  | 3.1. View Condominium Information Sections
2.5 | 0.45455 |  |  | 3.1.1. View All Non-Purchasable Documents for Condominium Information Section
3 | 0.54545 |  |  | 3.1.1.1. Edit Non-Purchasable Document
1 | 0.18182 |  |  | 3.1.1.2. Remove Non-Purchasable Document
4 | 0.72727 |  |  | 3.1.1.3. Add New Non-Purchasable Document
0 | 0 |  |  | 3.1.2. Add Condominium Information Section
0 | 0 |  |  | 3.1.3. Edit Condominium Information Section
0 | 0 |  |  | 3.1.4. Archive Condominium Information Section
6 | 1.0909 |  |  | 3.2. View Purchasable Document Categories
3.5 | 0.63636 |  |  | 3.2.1. View All Purchasable Documents for Purchasable Document Category
3 | 0.54545 |  |  | 3.2.1.1. Edit Purchasable Document
1 | 0.18182 |  |  | 3.2.1.2. Archive Purchasable Document
4 | 0.72727 |  |  | 3.2.1.3. Add New Purchasable Document
2.5 | 0.45455 |  |  | 3.3. View Important Contacts
3 | 0.54545 |  |  | 3.3.1. Add Important Contact
2.5 | 0.45455 |  |  | 3.3.2. View/Modify Important Contact
1 | 0.18182 |  |  | 3.3.3. Remove Important Contact
8 | 1.4545 |  |  | 3.4. View Condo Document Orders Report
2.5 | 0.45455 |  |  | 3.4.1. View Condo Document Order Details
Total Hours Estimate | 50
Total Days (Adj) | 9.0909
Condominium Building User Access Management
1.5 | 0.27273 |  |  | 4.1. Edit Assigned Condominium Building Users
0.5 | 0.090909 |  |  | 4.1.1. Show Pending Users (Currently in the Requested Condominium Access Queue)
3 | 0.54545 |  |  | 4.1.1.1. Approve Requested Access to Condominium Building
1 | 0.18182 |  |  | 4.1.1.2. Deny Requested Access to Condominium Building
0.5 | 0.090909 |  |  | 4.1.2. Show Active Users
0 | 0 |  |  | 4.1.2.1. Deactivate Condominium Building User
1 | 0.18182 |  |  | 4.1.3. Show Inactive Users
0 | 0 |  |  | 4.1.3.1. Activate Inactive Condominium Council Member/Condominium Building Unit Owner
Total Hours Estimate | 7.5
Total Days (Adj) | 1.3636
Condominium Building Search
6 | 1.0909 |  |  | 5.1. Search for Condominium Building
Total Hours Estimate | 6
Total Days (Adj) | 1.0909
Condominium Building Viewing (Public View)
8 | 1.4545 |  |  | 6.1. View Condominium Building Information
3 | 0.54545 |  |  | 6.2. View Condominium Building Rental Unit Information
3 | 0.54545 |  |  | 6.2.1. Submit Contact Inquiry to Rental Agent
2 | 0.36364 |  |  | 6.3. View Condominium Building Unit for Sale Information
1 | 0.18182 |  |  | 6.3.1. Submit Contact Inquiry to Purchase Agent
5 | 0.90909 |  |  | 6.4. Order Condominium Documents
13 | 2.3636 |  |  | 6.4.1. Select Document(s) to Order
12 | 2.1818 |  |  | 6.4.2. Pay for Document(s)
8 | 1.4545 |  |  | 6.4.3. Download Document(s)
Total Hours Estimate | 55
Total Days (Adj) | 10
Condominium Building Viewing (Condominium Building Unit Owner View)
7 | 1.2727 |  |  | 7.1. View Condominium Information for Condominium Building
0 | 0 |  |  | 7.1.1. Download Condominium Documents for Viewing Purposes
Total Hours Estimate | 7
Total Days (Adj) | 1.2727
Condominium Building Viewing (Condominium Council Member View)
3 | 0.54545 |  |  | 8.1. View Condominium Information for Condominium Building
0 | 0 |  |  | 8.1.1. Download Condominium Documents for Viewing Purposes
Total Hours Estimate | 3
Total Days (Adj) | 0.54545
Building Information Reporting
2 | 0.36364 |  |  | 9.1. Generate Building Summary Report (Enhanced Version)
3 | 0.54545 |  |  | 9.1.1. Generate Rental Building Summary Report
2 | 0.36364 |  |  | 9.1.2. Generate Condominium Building Summary Report
2 | 0.36364 |  |  | 9.1.3. Generate Commercial Building Report
4 | 0.72727 |  |  | 9.1.4. E-mail Summary Report
3 | 0.54545 |  |  | 9.1.5. Export Summary Report to CSV
3 | 0.54545 |  |  | 9.1.6. Print Summary Report
Total Hours Estimate | 19
Total Days (Adj) | 3.4545
Modifications to Existing Gateway Functionality
1 | 0.18182 |  |  | 10.1. Archive Residential Rental Building or Residential Building Unit
1.5 | 0.27273 |  |  | 10.2. Send Residential Rental Building to Trash
Total Hours Estimate | 2.5
Total Days (Adj) | 0.45455

## Use Case Totals
Hours Estimated | Days (Adj) | Time Spent | Over-Under | Use Case | 5.5 | Productivity Factor
General
1.5 | 0.27273 |  |  | 1.1. Condominium User Login (Condominium Council Member or Condominium Building Unit Owner)
5.5 | 1 |  |  | 1.2. Select Condominium Building Page
9 | 1.6364 |  |  | 1.3. Request Access to Condominium Building with Existing User Account
7 | 1.2727 |  |  | 1.4. Create New User Account and Request Access to Condominium Building
Total Hours Estimate | 23
Total Days (Adj) | 4.1818
Condominium Building and Unit Registration
8.5 | 1.5455 |  |  | 2.1. View Condominium Building and Unit Registration Page
10.5 | 1.9091 |  |  | 2.2. Create New Condominium Building
7.5 | 1.3636 |  |  | 2.3. View/Edit Existing Condominium Building
8.5 | 1.5455 |  |  | 2.3.1. Edit Condominium Building Photos
2 | 0.36364 |  |  | 2.3.2. Archive Condominium Building
3 | 0.54545 |  |  | 2.3.2.1. Send Condominium Building to Trash
8 | 1.4545 |  |  | 2.3.3. Edit Condominium Building Units
6.5 | 1.1818 |  |  | 2.3.3.1. New Condominium Building Unit
16 | 2.9091 |  |  | 2.3.3.2. Import Condominium Building Units from CSV
8 | 1.4545 |  |  | 2.3.3.3. View/Edit Existing Condominium Building Unit
7 | 1.2727 |  |  | 2.3.3.4. Edit Condominium Building Unit Photos
1.5 | 0.27273 |  |  | 2.3.3.5. Archive Condominium Building Unit
1 | 0.18182 |  |  | 2.3.3.6. Send Condominium Building Unit to Trash
6 | 1.0909 |  |  | 2.3.4. Search Archived Condominium Buildings
1.5 | 0.27273 |  |  | 2.3.5. Unarchive Archived Condominium Building
Total Hours Estimate | 95.5
Total Days (Adj) | 17.3636
Condominium Information Management
4.5 | 0.81818 |  |  | 3.1. View Condominium Information Sections |  |  |  | 9.5455 | MS2
4.5 | 0.81818 |  |  | 3.1.1. View All Non-Purchasable Documents for Condominium Information Section |  |  |  | 7.3636 | MS3
6 | 1.0909 |  |  | 3.1.1.1. Edit Non-Purchasable Document
2.5 | 0.45455 |  |  | 3.1.1.2. Remove Non-Purchasable Document
6.5 | 1.1818 |  |  | 3.1.1.3. Add New Non-Purchasable Document
0 | 0 |  |  | 3.1.2. Add Condominium Information Section
0 | 0 |  |  | 3.1.3. Edit Condominium Information Section
0 | 0 |  |  | 3.1.4. Archive Condominium Information Section
8 | 1.4545 |  |  | 3.2. View Purchasable Document Categories
7.5 | 1.3636 |  |  | 3.2.1. View All Purchasable Documents for Purchasable Document Category
7 | 1.2727 |  |  | 3.2.1.1. Edit Purchasable Document
2.5 | 0.45455 |  |  | 3.2.1.2. Archive Purchasable Document
8.5 | 1.5455 |  |  | 3.2.1.3. Add New Purchasable Document
4.5 | 0.81818 |  |  | 3.3. View Important Contacts
6 | 1.0909 |  |  | 3.3.1. Add Important Contact
6 | 1.0909 |  |  | 3.3.2. View/Modify Important Contact
2.5 | 0.45455 |  |  | 3.3.3. Remove Important Contact
13 | 2.3636 |  |  | 3.4. View Condo Document Orders Report
6 | 1.0909 |  |  | 3.4.1. View Condo Document Order Details
Total Hours Estimate | 95.5
Total Days (Adj) | 17.3636
Condominium Building User Access Management
4.5 | 0.81818 |  |  | 4.1. Edit Assigned Condominium Building Users
2 | 0.36364 |  |  | 4.1.1. Show Pending Users (Currently in the Requested Condominium Access Queue)
4.5 | 0.81818 |  |  | 4.1.1.1. Approve Requested Access to Condominium Building
2 | 0.36364 |  |  | 4.1.1.2. Deny Requested Access to Condominium Building
2 | 0.36364 |  |  | 4.1.2. Show Active Users
0.5 | 0.090909 |  |  | 4.1.2.1. Deactivate Condominium Building User
2.5 | 0.45455 |  |  | 4.1.3. Show Inactive Users
0.5 | 0.090909 |  |  | 4.1.3.1. Activate Inactive Condominium Council Member/Condominium Building Unit Owner
Total Hours Estimate | 18.5
Total Days (Adj) | 3.3636
Condominium Building Search
15.5 | 2.8182 |  |  | 5.1. Search for Condominium Building
Total Hours Estimate | 15.5
Total Days (Adj) | 2.8182
Condominium Building Viewing (Public View)
19 | 3.4545 |  |  | 6.1. View Condominium Building Information |  |  | 8.3636 | MS1
11.5 | 2.0909 |  |  | 6.2. View Condominium Building Rental Unit Information |  |  | 12.0909 | MS2
4.5 | 0.81818 |  |  | 6.2.1. Submit Contact Inquiry to Rental Agent
9 | 1.6364 |  |  | 6.3. View Condominium Building Unit for Sale Information
2 | 0.36364 |  |  | 6.3.1. Submit Contact Inquiry to Purchase Agent
12.5 | 2.2727 |  |  | 6.4. Order Condominium Documents
25 | 4.5455 |  |  | 6.4.1. Select Document(s) to Order
17 | 3.0909 |  |  | 6.4.2. Pay for Document(s)
12 | 2.1818 |  |  | 6.4.3. Download Document(s)
Total Hours Estimate | 112.5
Total Days (Adj) | 20.4545
Condominium Building Viewing (Condominium Building Unit Owner View)
17.5 | 3.1818 |  |  | 7.1. View Condominium Information for Condominium Building
0 | 0 |  |  | 7.1.1. Download Condominium Documents for Viewing Purposes
Total Hours Estimate | 17.5
Total Days (Adj) | 3.1818
Condominium Building Viewing (Condominium Council Member View)
6 | 1.0909 |  |  | 8.1. View Condominium Information for Condominium Building
0 | 0 |  |  | 8.1.1. Download Condominium Documents for Viewing Purposes
Total Hours Estimate | 6
Total Days (Adj) | 1.0909
Building Information Reporting
5 | 0.90909 |  |  | 9.1. Generate Building Summary Report (Enhanced Version)
8 | 1.4545 |  |  | 9.1.1. Generate Rental Building Summary Report
7 | 1.2727 |  |  | 9.1.2. Generate Condominium Building Summary Report
7 | 1.2727 |  |  | 9.1.3. Generate Commercial Building Report
7 | 1.2727 |  |  | 9.1.4. E-mail Summary Report
4 | 0.72727 |  |  | 9.1.5. Export Summary Report to CSV
5 | 0.90909 |  |  | 9.1.6. Print Summary Report
Total Hours Estimate | 43
Total Days (Adj) | 7.8182
Modifications to Existing Gateway Functionality
1 | 0.18182 |  |  | 10.1. Archive Residential Rental Building or Residential Building Unit
3.5 | 0.63636 |  |  | 10.2. Send Residential Rental Building to Trash
Total Hours Estimate | 4.5
Total Days (Adj) | 0.81818
Use Cases Total | 31381.8182 | 78.4545
Database Modifications | 1400
Testing and Deployment | 1600
Requirements Engineering | 2000
Grand Total | 36381.8182
MS1 | 28.5455 | C
MS2 | 21.6364 | IP
MS3 | 28.2727 | P
Total | 78.4545

## Summary
Component | Total Hours Estimate | Total Days (Adj) | Cost
General | 23 | 4.1818 | 1672.7273
Condominium Building and Unit Registration | 95.5 | 17.3636 | 6945.4545
Condominium Information Management | 95.5 | 17.3636 | 6945.4545
Condominium Building User Access Management | 18.5 | 3.3636 | 1345.4545
Condominium Building Search | 15.5 | 2.8182 | 1127.2727
Condominium Building Viewing (Public View) | 112.5 | 20.4545 | 8181.8182
Condominium Building Viewing (Condominium Building Unit Owner View) | 17.5 | 3.1818 | 1272.7273
Condominium Building Viewing (Condominium Council Member View) | 6 | 1.0909 | 436.3636
Building Information Reporting | 43 | 7.8182 | 3127.2727
Modifications to Existing Gateway Functionality | 4.5 | 0.81818 | 327.2727 | Use Case Total | 31381.8182
Database Modifications | 20 | 3.5 | 1400
Testing and Deployment | 40 | 4 | 1600
Requirements Engineering | 40 | 5 | 2000
Total Cost |  |  | 36381.8182
Presentable Components and Costs | Cost | Rounded
Condominium Building and Unit Registration | 6945.4545 | 7000
Condominium Information Management | 3145.4545 | 3150
Condominium Building User Access Management | 1345.4545 | 1350
Condominium Building Search | 1127.2727 | 1150
Condominium Building Viewing | 5040.9091 | 5050
Document Ordering | 8650 | 8650
Building Information Reporting | 3127.2727 | 3100
Modifications to Existing Gateway Functionality | 327.2727 | 350
General Framework and Database Modifications | 5072.7273 | 5000
Testing and Deployment | 1600 | 1600
Grand Total |  | 36400